Eastside Public Safety

Communications Agency

Executive Board

City of Bellevue

City of Kirkland

City of Redmond

City of Mercer Island

City of Issaquah

.

P O Box 97010 Mail Stop PSEPS, Redmond,WA 98073-9710 8701 160th Avenue NE, Redmond, WA 98052 tel (425) 556-2515 fax (425) 556-2517

# EXECUTIVE BOARD

SUMMARY OF MINUTES

March 9, 2023	                                Virtual Meeting

10:30 a.m.

PRESENT:	Kurt Triplett

ALTERNATES:  Malisa Files (Angela Birney), Jay Hagen (Brad Miyake)

ABSENT:  Paula Schwan, Jeff Magnan

OTHERS PRESENT:	Doug McDonald, Mark Hagreen, Kale Fong

1.	Call to Order

The meeting was called to order at 10:34 a.m. by Kurt Triplett, who presided.

- Roll Call

3.	Approve Agenda

Malisa Files motioned to approve the agenda, it was seconded by Jay Hagen and carried 3-0.

4.	Consent Agenda

a) Approval of the minutes of December 8, 2022

b) Approval of payment vouchers and credit card purchases

Malisa Files motioned to approve the Consent Agenda, it was seconded by Jay Hagen and

carried 3-0.

5.     Action

6.	Reports

a) PSERN report – Mark Hagreen

Mark Hagreen presented a slide presentation which provided an overview of PSERN’s budget, scheduling timelines, DAS migration process and project risks.  The radio deployment effort is behind schedule.  EPSCA was slated for completion in June 2023 but it has changed to TBD.  The decommissioning process is in the planning stages.  EPSCA hopes to decommission West Tiger before winter to save on leasing costs.  Full System Acceptance is still slated for December 2023.  PSERN is requesting an additional depot location for the greater Redmond/Bellevue/

Kirkland area.  Not all DAS will be migrated in time for the transition.  A priority list is being created.

b) EPSCA – Mark Hagreen

Mark Hagreen reported the Norway Tower equipment move is complete. EPSCA continues the “monitor and adjust” approach to Education Hill. At Full System Acceptance, EPSCA will discontinue charging subscribers for service and will not have revenue for 2024.  We will need to utilize reserves. Dissolution is projected to begin in mid-2024/early 2025. Kurt Triplett reminded the Board members that EPSCA will continue as a selection agency.

7.     Other/Information

8.	Executive Session - None

9.	Adjourn

Being no further business, meeting ended at 11:13 a.m.

Next Meeting

Calendared for

April 13, 2023